Annual (April 1, 2014 to March 31, 2015) Performance Evaluation Report in respect of RFD 2014-2015 of RSCs i.e. Institutes

Name of the Division: 	Animal Science Division

Name of the Institution: 	ICAR - Central Sheep and Wool Research Institute, Avikanagar

RFD Nodal Officer: 		Dr C.P. Swarnkar, Scientist (SG)

| S. No. | Objective (s) | Weight | Action (s) | Success Indicator (s) | Unit | Weight | Target / Criteria Value |  |  |  |  | Achievements | Performance |  | Percent achievements against Target values of 90% Col. | Reasons for shortfalls or excessive achievements, if applicable |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Excellent 100% | Very Good 90% | Good 80% | Fair 70% | Poor 60% |  | Raw Score | Weighted Score |  |  |
| 1 | Productivity enhancement of sheep for mutton and wool | 50 | Increase mutton and wool production | Supply of superior breeding rams and bucks | No. | 17 | 192 | 160 | 128 | 96 | 64 | 347 | 100 | 17 | 216.9 | Higher demand from developmental agencies |
|  |  |  |  | Development of feed supplements | No. | 11 | 3 | 2 | 1 | 0 | 0 | 3 | 100 | 11 | 150.0 | Successful in achieving 100% target |
|  |  |  |  | Artificial insemination (AI) in sheep | No. | 11 | 240 | 200 | 160 | 120 | 80 | 226 | 96.5 | 10.62 | 113.0 | - |
|  |  |  |  | Sheep covered under health management technology | No. | 7 | 11040 | 9200 | 7360 | 5520 | 3680 | 9410 | 91.1 | 6.38 | 102.3 | - |
|  |  |  |  | Screening of samples for disease diagnosis | No. | 4 | 14400 | 12000 | 9600 | 7200 | 4800 | 15621 | 100 | 4 | 130.2 | Incorporation of activity of new network programme |
| 2 | Value addition and post harvest technology for meat and wool | 20 | Increase value added products | Products/process of wool and specialty hair developed | No. | 12 | 3 | 2 | 1 | 0 | 0 | 3 | 100 | 12 | 150.0 | Successful in achieving 100% target. |
|  |  |  |  | Products/process of mutton developed | No. | 8 | 3 | 2 | 1 | 0 | 0 | 2 | 90 | 7.2 | 100.0 | - |
| 3 | Transfer of technology | 10 | Exhibitions, field days, health camps, goshtis, trainings | Conduct of demonstration | No. | 10 | 41 | 34 | 27 | 20 | 13 | 35 | 91.4 | 9.14 | 102.9 | - |
|  | Publication/Documentation | 5 | Publication of the research articles in the journals having the NAAS rating of 6.0 and above | Research articles published | No. | 3 | 24 | 20 | 16 | 12 | 8 | 21 | 92.5 | 2.78 | - | - |
|  |  |  | Timely publication of the Institute Annual Report (2013-2014) | Annual Report published | Date | 2 | June 30, 2014 | July 02, .2014 | July 04, 2014 | July 07, 2014 | July 09, 2014 | June 26, 2014 | 100 | 2 | - | - |
|  | Fiscal resource management | 2 | Utilization of released plan fund | Plan fund utilized | % | 2 | 98 | 96 | 94 | 92 | 90 | 98.9 | 100 | 2 | - | - |
|  | Efficient Functioning of the RFD System | 3 | Timely submission of Draft RFD for 2014-2015 for Approval | On-time submission | Date | 2 | May 15, 2014 | May 16, 2014 | May 19, 2014 | May 20, 2014 | May 21, 2014 | April 27, 2014 | 100 | 2 | - | - |
|  |  |  | Timely submission of Results for 2013-2014 | On-time submission | Date | 1 | May 1 2014 | May 2 2014 | May 5 2014 | May 6 2014 | May 7 2014 | April 27, 2014 | 100 | 1 | - | - |
|  | Enhanced Transparency / Improved Service delivery of Ministry/Department | 3 | Rating from Independent Audit of implementation of Citizens’ / Clients’ Charter (CCC) Independent Audit of implementation of Grievance Redress Management (GRM) system | Degree of implementation of commitments in CCC | % | 2 | 100 | 95 | 90 | 85 | 80 | 100 | 100 | 2 | - | - |
|  |  |  |  | Degree of success in implementing GRM | % | 1 | 100 | 95 | 90 | 85 | 80 | 100 | 100 | 1 | - | - |
|  | Administrative Reforms | 7 | Update organizational strategy to align with revised priorities | Date | Date | 2 | Nov. 1, 2014 | Nov. 2, 2014 | Nov. 3, 2014 | Nov. 4, 2014 | Nov. 5, 2014 | Sep 23, 2014 | 100 | 2 | - | - |
|  |  |  | Implementation of agreed milestones of approved Mitigating Strategies for Reduction of potential risk of corruption (MSC) | % of Implementation | % | 1 | 100 | 90 | 80 | 70 | 60 | 100 | 100 | 1 | - | - |
|  |  |  | Implementation of agreed milestones for ISO 9001 | % of implementation | % | 2 | 100 | 95 | 90 | 85 | 80 | 100 | 100 | 2 | - | - |
|  |  |  | Implementation of milestones of approved Innovation Action Plans (IAPs) | % of implementation | % | 2 | 100 | 90 | 80 | 70 | 60 | 100 | 100 | 2 | - | - |

Total Composite Score: 97.12

Rating: Excellent

ANNEXURE-I

Actual Scientific Staff in position in the Institute and their research articles publications published in International and National Journals having NAAS rating 6.00 or more during April 1, 2014-March 31, 2015

Name of the Division: Animal Science

Name of the Institute: ICAR – Central Sheep and Wool Research Institute

| S.No. | Category of Scientific Staff | Actual Scientific Staff in position (Nos.) | Research articles publications as first /corresponding author (Nos.) | Publication productivity (Number of research articles publications divided by number of Scientists) |
| --- | --- | --- | --- | --- |
|  | Principal Scientist | 15 | 06 | 0.40 |
|  | Senior Scientist | 11 | 01 | 0.09 |
|  | Scientist | 23 | 14 | 0.61 |
| Total |  | 49 | 21 | 0.43 |