Results Framework Document R F D

for

Central Sheep and Wool Research Institute

(April 1, 2013 to March 31, 2014)

Avikanagar 304 501 Rajasthan

(http://www.cswri.res.in)

Annual (April 1, 2013 to March 31, 2014) Performance Evaluation Report in respect of RFD 2013-2014 of RSCs i.e. Institutes

Name of the Division: 	Animal Science Division

Name of the Institution: 	Central Sheep and Wool Research Institute, Avikanagar

RFD Nodal Officer: 		Dr C.P. Swarnkar, Scientist (SG)

| S. No. | Objective (s) | Weight | Action (s) | Success Indicator (s) | Unit | Weight | Target / Criteria Value |  |  |  |  | Achievements | Performance |  | Percent achievements against Target values of 90% Col. | Reasons for shortfalls or excessive achievements, if applicable |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Excellent 100% | Very Good 90% | Good80% | Fair 70% | Poor 60% |  | Raw Score | Weighted Score |  |  |
| 1 | Enhancement of sheep productivity for mutton and wool | 50 | Increase mutton and wool production | Supply of superior breeding rams (Malpura, Magra and Marwari) | Number | 15 | 100 | 90 | 80 | 70 | 60 | 154 | 100 | 15 | 171.1 | Higher demand from developmental agencies. |
|  |  |  |  | Development of feed supplements | Number | 15 | 3 | 2 | 1 | 0 | 0 | 3 | 100 | 15 | 150 | Successful in achieving 100% target. |
|  |  |  |  | Artificial insemination (AI) in field flocks | Number | 10 | 200 | 180 | 160 | 140 | 120 | 226 | 100 | 10 | 125.6 | Increased demand from farmers. |
|  |  |  |  | Sheep covered under health management technology in field and farm | Number | 10 | 7000 | 6300 | 5600 | 4900 | 4200 | 9393 | 100 | 10 | 149.1 | Increase in flock number and dynamic nature of flocks in adopted villages. |
| 2 | Value addition of mutton and wool | 25 | Increase value added products | Products/process of wool and specialty hair developed | Number | 15 | 3 | 2 | 1 | 0 | 0 | 3 | 100 | 15 | 150 | Successful in achieving 100% target. |
|  |  |  |  | Products/process of mutton developed | Number | 10 | 3 | 2 | 1 | 0 | 0 | 2 | 90 | 9 | 100 | - |
| 3 | Transfer of technology | 14 | Exhibitions field day, health camps and trainings | Conduct of demonstration | Number | 14 | 36 | 32 | 29 | 25 | 22 | 37 | 100 | 14 | 115.6 | - |
|  | Efficient functioning of the RFD system | 3 | Timely submission of RFD for 2013-14 | On-time submission | Date | 2 | 15 May 2013 | 16 May 2013 | 17 May 2013 | 20 May 2013 | 21 May 2013 | 6 May 2013 | 100 | 2 | - | - |
|  |  |  | Timely submission of results for 2012-13 | On-time submission | Date | 1 | 1 May 2013 | 2 May 2013 | 5 May 2013 | 6 May 2013 | 7 May 2013 | 15 April 2013 | 100 | 1 | - | - |
|  | Administrative reforms | 4 | Implement ISO 9001 as per approved action plan | % implementation | % | 2 | 100 | 95 | 90 | 85 | 80 | 100 | 100 | 2 | - |  |
|  |  |  | Prepare an action plan for innovation | On time submission | Date | 2 | 30 Jul 2013 | 10 Aug 2013 | 20 Aug 2013 | 30 Aug 2013 | 10 Aug 2013 | 26 Jul 2013 | 100 | 2 | - |  |
|  | Improving internal efficiency / responsiveness / service delivery of Ministry / Department | 4 | Implementation of Sevottam | Independent audit of implementation of Citizen’s Charter | % | 2 | 100 | 95 | 90 | 85 | 80 | 100 | 100 | 2 | - |  |
|  |  |  |  | Independent audit of implementation of public grievance redressal system | % | 2 | 100 | 95 | 90 | 85 | 80 | 100 | 100 | 2 | - |  |

Total Composite Score: 99.0

Rating: Excellent

Annexure-I

Details of achievement for RFD 2013-14

| S.No. | Success indicators | Achievements | Remarks |
| --- | --- | --- | --- |
| 1 | Supply of superior breeding rams (Malpura, Magra and Marwari) | Supplied 154 breeding rams to developmental agencies and farmers | Malpura (50), Magra (84) and Marwari (20) |
| 2 | Development of feed supplements | - Azolla feeding in lambs - Rumen bypass fat - Feeding of oont catela (Blepharis indica) in lactating ewes | Azolla successfully replace 10% of concentrate moiety in diet without effecting lamb performance Rumen bypass fat at 4% level of supplementation in concentrate ration for higher body weight, body condition score and carcass yield Feeding of oont catela (Blepharis indica) @ 281 g DM/day in ewes resulted in 88-177 g/day higher milk yield at 30 and 60 days of parturition |
| 3 | Artificial insemination (AI) in field flocks | Performed 226 AI in field flocks | AI was done using fresh diluted semen from elite rams |
| 4 | Sheep covered under health management technology in field and farm | Provided health coverage to an average of 9395 sheep (farm and field) | Preventive measures were undertaken as per planned flock health approach including vaccination against enterotoxaemia (22204), sheep pox (12705), PPR (8722) and FMD (9364) anthelmintic drenching (10680), dipping (2870) and foot bath (4700) |
| 5 | Products/process of wool and specialty hair developed | - Development of 100% Angora fabric for apparel purposes - Development of insulative protective cloth for cold region - Development of geo-textiles using wool felt | PVA was used as carrier fibre to produce pure angora fabric with 2/2 twill weave on hand loom. Six layer sandwich fabric (coated fabric + 4 layers of Bharat Merino wool + polyester) was developed as a protective clothing. Thermal insulation (Tog) value of 15 was obtained with weight of 1160 g/m2. Wool geo-textile retained up to 20% moisture in soil and with 15% higher yield of barley and pea crops. |
| 6 | Products/process of mutton developed | - Low fat mutton nuggets - Tenderization protocol for meat | Low fat mutton nuggets were developed and accepted up to 18 days at refrigeration storage Tenderization protocol for meat of cull ewes using plant proteases |
| 7 | Conduct of demonstration | Exhibitions, field day, health camps and trainings | Demonstrated technologies in sheep production through exhibitions (11), AI (4), fodder production (1), supplementary feeding (2), health camps (9), field days, Ghosti and trainings (10) |